## Sheet1
Task Number. | Task Description | Category/Feature | Priority | Assigned to | Collaboraters | Start Date | Due Date | Completion Date | Estimated Hours | Actual Hors | Reviewer | Review Status | Task Status
1 | Bakend API for even search with filters | Backend | 1 | Ali | N/A | 2025-09-13 | 2025-10-12 | N/A | 10 | N/A | N/A | N/A | InProgress
2 | Frontend search and connect results to backend | Frontend | 3 | Ali | N/A | 2025-09-13 | 2025-10-12 | N/A | 6 | N/A | N/A | N/A | InProgress
3 | Event list page layout | Frontend | 2 | Ali | N/A | 2025-09-13 | 2025-10-12 | N/A | 8 | N/A | N/A | N/A | InProgress
4 | Sort and filter options | Backend | 2 | Ali | N/A | 2025-09-13 | 2025-10-12 | N/A | 4 | N/A | N/A | N/A | InProgress
5 | Save to calendar | Frontend/Backend | 1 | Shayan | N/A | 2025-09-13 | 2025-10-12 | N/A | 1 | N/A | N/A | N/A | InProgress
6 | Store saved events in database | DataBase | 2 | Shayan | N/A | 2025-09-13 | 2025-10-12 | N/A | 2 | N/A | N/A | N/A | InProgress
7 | Backend route for claiming tickets | Backend | 3 | Shayan | N/A | 2025-09-13 | 2025-10-12 | N/A | 5 | N/A | N/A | N/A | InProgress
8 | Claim Ticket button | Frontend | 1 | Shayan | N/A | 2025-09-13 | 2025-10-12 | N/A | 6 | N/A | N/A | N/A | InProgress
9 | Show claimed tickets in student dashboard | Frontend | 2 | Ryan | N/A | 2025-09-13 | 2025-10-12 | N/A | 9 | N/A | N/A | N/A | InProgress
10 | Generate unique QR codes for tickets | Frontend/Backend | 2 | Ryan | N/A | 2025-09-13 | 2025-10-12 | N/A | 7 | N/A | N/A | N/A | InProgress
11 | Display QR codes in student dashboard | Frontend | 2 | Ryan | N/A | 2025-09-13 | 2025-10-12 | N/A | 2 | N/A | N/A | N/A | InProgress
12 | Event creation form | Frontend | 3 | Ryan | N/A | 2025-09-13 | 2025-10-12 | N/A | 1 | N/A | N/A | N/A | InProgress
13 | Route to save new events | Backend | 3 | Davan | N/A | 2025-09-13 | 2025-10-12 | N/A | 4 | N/A | N/A | N/A | InProgress
14 | Validate event inputs | Backend | 3 | Davan | N/A | 2025-09-13 | 2025-10-12 | N/A | 2 | N/A | N/A | N/A | InProgress
15 | Ticket counter statistics | Backend | 2 | Davan | N/A | 2025-09-13 | 2025-10-12 | N/A | 3 | N/A | N/A | N/A | InProgress
16 | Organizer dashboard with analytics | Frontend | 2 | Davan | Rayn | 2025-09-13 | 2025-10-12 | N/A | 14 | N/A | N/A | N/A | InProgress
17 | CSV export of attendee list | Frontend/Backend | 2 | Omar | N/A | 2025-09-13 | 2025-10-12 | N/A | 10 | N/A | N/A | N/A | InProgress
18 | Download button in organizer dashboard | Backend | 3 | Omar | N/A | 2025-09-13 | 2025-10-12 | N/A | 4 | N/A | N/A | N/A | InProgress
19 | QR scanner integration | Frontend | 2 | Omar | N/A | 2025-09-13 | 2025-10-12 | N/A | 2 | N/A | N/A | N/A | InProgress
20 | Endpoint for QR validation | Backend | 2 | Shayan | N/A | 2025-09-13 | 2025-10-12 | N/A | 3 | N/A | N/A | N/A | InProgress
21 | Approval page | Frontend | 3 | Nirthika | N/A | 2025-09-13 | 2025-10-12 | N/A | 6 | N/A | N/A | N/A | InProgress
22 | Route for approval | Backend | 3 | Shayan | N/A | 2025-09-13 | 2025-10-12 | N/A | 7 | N/A | N/A | N/A | InProgress
23 | Moderate event listings | Frontend/Backend | 3 | Ali | N/A | 2025-09-13 | 2025-10-12 | N/A | 8 | N/A | N/A | N/A | InProgress
24 | Remove flagged events from database | DataBase | 3 | Nirthika | N/A | 2025-09-13 | 2025-10-12 | N/A | 7 | N/A | N/A | N/A | InProgress
25 | Queries for global analytics | Backend | 1 | Omar | Shayan | 2025-09-13 | 2025-10-12 | N/A | 18 | N/A | N/A | N/A | InProgress
26 | Admin dashboard for global stats | Frontend | 2 | Ali | N/A | 2025-09-13 | 2025-10-12 | N/A | 5 | N/A | N/A | N/A | InProgress
27 | Manage organizations and roles | Backend | 1 | Nirthika | N/A | 2025-09-13 | 2025-10-12 | N/A | 4 | N/A | N/A | N/A | InProgress
28 | Update database for role changes | DataBase | 1 | Ali | N/A | 2025-09-13 | 2025-10-12 | N/A | 5 | N/A | N/A | N/A | InProgress